## Project schedule
| CIVE 202 Project #3 | [5 empty] | Project start: | [7 empty] | 2026-02-26 | [33 empty] | DEPENDENCIES
| Jacob Oetken | [5 empty] | Display week: | [7 empty] | 1 | [34 empty] | Right Symbol is Dependent Upon Left Symbol
[7 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-20
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2026-02-23 to 2026-04-05
 | time axis 2026-02-23 to 2026-04-05
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| Github Repository | [47 empty] | FINAL REPORT | GITHUB REPO | CODE DOCUMENT | ANNOTATED CD
| Create Github | Jacob Oetken | 0% | 2026-02-26 | 2026-02-26 | 1
| Create README Document | Jacob Oetken | 0% | 2026-02-26 | 2026-03-20 | 23
| Combine information/Files | Jacob Oetken | 0% | 2026-03-20 | 2026-03-27 | 8
| Upload All Files to Github | Jacob Oetken | 0% | 2026-03-24 | 2026-03-27 | 4
| Submit | Jacob Oetken | 0% | 2026-03-27 | 2026-03-31 | 5
Scope of Work
| Identify Tasks | Jacob Oetken | 0% | 2026-02-24 | 2026-02-26 | 3
| Create SOW | Jacob Oetken | 0% | 2026-02-25 | 2026-03-03 | 7
| Identify Variables (NHTS and NGSIM) | Jacob Oetken | 0% | 2026-02-28 | 2026-03-04
| Describe Sources | Jacob Oetken | 0% | 2026-03-01 | 2026-03-05 | 5
| Review | Jacob Oetken | 0% | 2026-03-05 | 2026-03-06 | 2
| Submit SOW | Jacob Oetken | 0% | 2026-03-06 | 2026-03-07 | 2
Gantt Chart
| Identify Tasks | Jacob Oetken | 100% | 2026-02-23 | 2026-02-25 | 3
| Create Gantt Chart | Jacob Oetken | 100% | 2026-02-25 | 2026-02-26 | 2
| Assign Durrations of Tasks | Jacob Oetken | 100% | 2026-02-26 | 2026-02-26
| Review | Jacob Oetken | 100% | 2026-02-26 | 2026-02-27 | 2
| Turn in Gantt Chart | Jacob Oetken | 100% | 2026-02-27 | 2026-02-27 | 1
Data Analysis and Preparation
| Review NHTS Metadata | Jacob Oetken | 0%
| Review NGSIM Metadata | Jacob Oetken | 0%
| Select Variables for Plotting | Jacob Oetken | 0%
| Clean NHTS Data | Jacob Oetken | 0%
| Clean NGSIM Data | Jacob Oetken | 0%
| Create Subsets | Jacob Oetken | 0%
Python Code
| LAB 1 Material | Jacob Oetken | 0% | 2026-02-27 | 2026-03-06 | 8
| LAB 2 Material | Jacob Oetken | 0% | 2026-03-06 | 2026-03-13
| LAB 3 Material | Jacob Oetken | 0% | 2026-03-13 | 2026-03-27
| LAB 4 Material | Jacob Oetken | 0% | 2026-03-27 | 2026-03-31
| Combine/Polish | Jacob Oetken | 0% | 2026-03-28 | 2026-03-31
| Review and Submit | Jacob Oetken | 0% | 2026-03-31 | 2026-03-31
Annotated Code Document
| Bar Chart Section | Jacob Oetken | 0%
| Histogram Section | Jacob Oetken | 0%
| Box Plot Section | Jacob Oetken | 0%
| Time Series Section | Jacob Oetken | 0%
| IDM Section | Jacob Oetken | 0%
| Combine/Polish | Jacob Oetken | 0% | 2026-03-29 | 2026-03-31
| Review and Submit | Jacob Oetken | 0% | 2026-03-31 | 2026-03-31
Written Report
| Analyze Visualization Outputs | Jacob Oetken | 0%
| Intepret Transportation Trends | Jacob Oetken | 0%
| Interpret Driving Behavior (NGSIM) | Jacob Oetken | 0%
| Interpret IDM Simulation(s) | Jacob Oetken | 0%
| Create Document | Jacob Oetken | 0% | 2026-03-27 | 2026-03-27
| Report Findings | Jacob Oetken | 0% | 2026-03-27 | 2026-03-29
| Review | Jacob Oetken | 0% | 2026-03-29 | 2026-03-31
| Submit | Jacob Oetken | 0% | 2026-03-31 | 2026-03-31
Formulas:
Project start: = [Project start:, row below]
R
R
R
_
_
R
R
R
G
G
G
G
C
C
A
C
A
DATES DUE ARE UNKNOWN, WILL ADJUST ONCE DATES ARE GIVEN (this is a draft - will be updated for final)
G
DATES DUE ARE UNKNOWN, WILL ADJUST ONCE DATES ARE GIVEN (this is a draft - will be updated for final)
DATES DUE ARE UNKNOWN, WILL ADJUST ONCE DATES ARE GIVEN (this is a draft - will be updated for final)
DATES DUE ARE UNKNOWN, WILL ADJUST ONCE DATES ARE GIVEN (this is a draft - will be updated for final)